## Blank Template
SH | SIMPLICITYHUB® STAKEHOLDER ANALYSIS |  |  |  | PRACTICAL TEMPLATE
Identify stakeholders and plan engagement based on influence and interest. |  |  |  |  | STAKEHOLDER ANALYSIS
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS STAKEHOLDER ANALYSIS? | A Stakeholder Analysis identifies everyone affected by or involved in your project. It helps you understand their level of influence and interest so you can engage the right people in the right way.
Name / Group | Department / Org | Influence | Interest | Position | Engagement Strategy
simplicityhub.co.uk |  |  | STAKEHOLDER ANALYSIS ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB® STAKEHOLDER ANALYSIS |  |  |  | PRACTICAL TEMPLATE
Identify stakeholders and plan engagement based on influence and interest. |  |  |  |  | STAKEHOLDER ANALYSIS
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS STAKEHOLDER ANALYSIS? | A Stakeholder Analysis identifies everyone affected by or involved in your project. It helps you understand their level of influence and interest so you can engage the right people in the right way.
Name / Group | Department / Org | Influence | Interest | Position | Engagement Strategy
Sarah Mitchell | Director Level | High | High | Champion | Monthly exec updates; involve in key decisions and approvals
James Carter | Operations | High | High | Champion | Daily project lead; owns scope and delivery decisions
Sarah Ahmed | Customer Service | Medium | High | Supporter | Core team member; weekly check-ins and design workshops
Tom Barker | IT | Medium | Medium | Neutral | Bi-weekly updates; involve early in technical design phase
Louise Chen | QA | Medium | High | Supporter | Core team member; owns quality and compliance sign-off
Front-line agents | Customer Service | Low | High | Neutral | Group briefings; feedback surveys; team lead cascade
Finance team | Finance | Low | Low | Neutral | Quarterly ROI updates; align to month-end reporting
Legal/Compliance | Compliance | Low | Low | Neutral | Inform of process changes requiring compliance review
simplicityhub.co.uk |  |  | STAKEHOLDER ANALYSIS ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html