## Blank Template
SH | SIMPLICITYHUB® ACTION PLAN |  |  |  | PRACTICAL TEMPLATE
Track actions, owners, priorities, due dates, dependencies and completion status. |  |  |  |  | ACTION PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS ACTION PLAN? | An Action Plan is a structured record of all tasks needed to implement the solution. For each action, record a clear description, the accountable owner, priority, due date, any dependencies and current status. Review regularly to track progress and remove blockers.
Total actions | 0 | Complete | 0 of 0 | Overall progress | 0%
ACTION REGISTER |  |  | Track all actions, owners, priorities and status
# | Action | Owner | Priority | Due Date | Dependencies | Status | Progress | Notes
simplicityhub.co.uk |  |  | Action Plan ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB® ACTION PLAN |  |  |  | PRACTICAL TEMPLATE
Track actions, owners, priorities, due dates, dependencies and completion status. |  |  |  |  | ACTION PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS ACTION PLAN? | An Action Plan is a structured record of all tasks needed to implement the solution. For each action, record a clear description, the accountable owner, priority, due date, any dependencies and current status. Review regularly to track progress and remove blockers.
Total actions | 8 | Complete | 1 of 8 | Overall progress | 28%
ACTION REGISTER |  |  | Track all actions, owners, priorities and status
# | Action | Owner | Priority | Due Date | Dependencies | Status | Progress | Notes
1 | Design and embed investigation checklist in CRM closure screen | James Carter | Critical | 07 Apr 2026 | — | In Progress | 40% | Template drafted; CRM config pending
2 | Redesign closure process to require root cause coding | James Carter | High | 14 Apr 2026 | 1 | Not Started | 0% | Awaiting checklist sign-off
3 | Develop and embed standard closure communication script | Sarah Ahmed | High | 10 Apr 2026 | — | In Progress | 60% | Draft v2 in review with TLs
4 | Publish authority level guide and distribute to team | James Carter | High | 04 Apr 2026 | — | Complete | 100% | Distributed 02 Apr 2026
5 | Develop real-time SLA alert and dashboard in CRM | IT Lead | High | 30 Apr 2026 | — | Not Started | 0% | IT sprint planning w/c 07 Apr
6 | Launch agent refresher training programme | L&D Lead | Medium | 21 Apr 2026 | 1, 3 | Not Started | 0% | L&D brief submitted
7 | CRM-email channel integration project kick-off | IT Lead | High | 14 Apr 2026 | — | In Progress | 20% | Discovery phase underway
8 | Improve CSAT survey trigger timing | IT Lead | Medium | 28 Apr 2026 | 7 | Not Started | 0% | Depends on CRM integration work
simplicityhub.co.uk |  |  | Action Plan ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html