## Blank Template
SH | SIMPLICITYHUB® PILOT PLAN TEMPLATE |  |  |  | PRACTICAL TEMPLATE
Define the scope, activities, success criteria and risks for a controlled pilot of your solution. |  |  |  |  | PILOT PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS PILOT PLAN? | A Pilot Plan defines the parameters for a controlled trial of a proposed solution. It establishes the pilot scope, objective, success criteria, key activities, data to be collected and the Go/No-Go decision criteria — ensuring the pilot generates valid, actionable results before full-scale implementation.
PILOT SUMMARY
Pilot Name
Pilot Owner
Location / Scope
Duration
Objective
Scope (in / out)
SUCCESS CRITERIA |  |  | Define measurable targets the pilot must meet
Metric / Success Criterion | Target | Current Baseline
KEY ACTIVITIES |  |  | Ordered list of pilot activities with owner and dates
# | Activity | Owner | Start Date | End Date | Notes
1
2
3
4
5
DATA TO COLLECT DURING PILOT
PILOT RISKS AND MITIGATIONS
Risk |  | Mitigation / Contingency
GO / NO-GO DECISION CRITERIA
simplicityhub.co.uk |  |  | Pilot Plan Template ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB® PILOT PLAN TEMPLATE |  |  |  | PRACTICAL TEMPLATE
Define the scope, activities, success criteria and risks for a controlled pilot of your solution. |  |  |  |  | PILOT PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS PILOT PLAN? | A Pilot Plan defines the parameters for a controlled trial of a proposed solution. It establishes the pilot scope, objective, success criteria, key activities, data to be collected and the Go/No-Go decision criteria — ensuring the pilot generates valid, actionable results before full-scale implementation.
PILOT SUMMARY
Pilot Name | Structured Investigation Checklist — Controlled Pilot
Pilot Owner | James Carter
Location / Scope | Customer Service Team A (6 agents)
Duration | 2 weeks (01 Apr – 14 Apr 2026)
Objective | Validate that the investigation checklist reduces average response time and repeat contact rate in a controlled group before full deployment.
Scope (in / out) | Team A (6 agents), all complaint types except tier-2 escalations, over a 2-week period.
SUCCESS CRITERIA |  |  | Define measurable targets the pilot must meet
Metric / Success Criterion | Target | Current Baseline
Average complaint response time | ≤ 3.5 days | 5.2 days
Repeat contact rate | ≤ 30% | 38%
Customer CSAT score | ≥ 72% | 67%
Agent usability rating | ≥ 4 / 5 | N/A — new process
KEY ACTIVITIES |  |  | Ordered list of pilot activities with owner and dates
# | Activity | Owner | Start Date | End Date | Notes
1 | Week 0 — Team A briefing and checklist training | James Carter | 28 Mar 2026 | 31 Mar 2026 | Briefing pack and demo
2 | Week 1–2 — Live pilot with daily data capture | James Carter | 01 Apr 2026 | 14 Apr 2026 | Daily CRM data pull
3 | Week 2 — Mid-point check-in and adjustment | James Carter | 07 Apr 2026 | 07 Apr 2026 | TL debrief; flag any issues
4 | Data collation and statistical analysis | Data Analyst | 14 Apr 2026 | 17 Apr 2026 | Compare pilot vs control
5 | Go/No-Go decision and executive review | Sarah Mitchell | 18 Apr 2026 | 18 Apr 2026 | Present results to sponsor
DATA TO COLLECT DURING PILOT
Response time per case (CRM), repeat contact flag, CSAT score, FCR flag, agent usability feedback (daily survey).
PILOT RISKS AND MITIGATIONS
Risk |  | Mitigation / Contingency
Pilot group volume higher than usual — confounds results |  | Pre-assess volume; scale scope if needed; flag in analysis
Agents revert to old habits without observation |  | Daily check-in; TL observation; weekly debrief
Confounding factors (bank holidays, volume spikes) |  | Exclude outlier weeks in analysis; document all anomalies
GO / NO-GO DECISION CRITERIA
At least 2 of 3 KPI success criteria met; no significant adverse customer feedback reported during the pilot period.
simplicityhub.co.uk |  |  | Pilot Plan Template ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html