## Blank Template
SH | SIMPLICITYHUB® CONTROL PLAN |  |  |  | PRACTICAL TEMPLATE
Specify how each CTQ will be measured, controlled and what the reaction plan is if it goes out of specification. |  |  |  |  | CONTROL PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS CONTROL PLAN? | A Control Plan documents how each Critical-to-Quality (CTQ) characteristic will be measured, monitored and controlled after improvement. For each process step, define the CTQ, the specification or target, how it is measured, how frequently, the sample size, the control method (e.g. control chart, CRM alert, audit), the owner, and the reaction plan to follow if the CTQ goes out of specification.
CONTROL PLAN REGISTER |  |  | Complete one row per CTQ / process step
Process Step | CTQ / Characteristic | Specification / Target | Measurement Method | Frequency | Sample Size | Control Method | Owner | Reaction Plan (if out of spec)
simplicityhub.co.uk |  |  | Control Plan ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB® CONTROL PLAN |  |  |  | PRACTICAL TEMPLATE
Specify how each CTQ will be measured, controlled and what the reaction plan is if it goes out of specification. |  |  |  |  | CONTROL PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS CONTROL PLAN? | A Control Plan documents how each Critical-to-Quality (CTQ) characteristic will be measured, monitored and controlled after improvement. For each process step, define the CTQ, the specification or target, how it is measured, how frequently, the sample size, the control method (e.g. control chart, CRM alert, audit), the owner, and the reaction plan to follow if the CTQ goes out of specification.
CONTROL PLAN REGISTER |  |  | Complete one row per CTQ / process step
Process Step | CTQ / Characteristic | Specification / Target | Measurement Method | Frequency | Sample Size | Control Method | Owner | Reaction Plan (if out of spec)
1 — Complaint receipt & acknowledgement | Acknowledgement time | ≤ 4 hours from receipt | CRM timestamp (case open → ack sent) | Daily auto-report | All cases | CRM SLA alert + real-time dashboard | CS Team Lead | If ≥ 5 breaches in one day: investigate reason and escalate to manager
2 — Investigation (checklist) | Checklist completion rate | 100% of cases | CRM mandatory completion field | Real-time (CRM) | All cases | CRM mandatory field — cannot close case without completing | CS Agent / Team Lead | If rate drops below 95%: TL spot-check + coaching session within 2 days
3 — Resolution & closure | Time to resolution (TTR) | ≤ 3.5 days average | CRM case open → close date | Weekly I-MR chart | All closed cases | I-MR Control Chart on TTR — reviewed weekly | Process Owner | 3 consecutive points above UCL: RCA and escalate to CS manager
4 — Root cause coding | Root cause recorded at closure | 100% of closed cases coded | CRM closure screen mandatory field | Monthly audit sample (n=30) | 30 sampled cases | CRM mandatory field + monthly audit | CS Agent / CS Team Lead | If >5% uncoded in audit: system alert + TL review + coaching
5 — CSAT survey | Customer satisfaction score (CSAT) | ≥ 72% (target; current 67%) | Post-resolution CSAT survey | Monthly average | Target ≥ 50% response rate | Monthly run chart — Process Owner reviews | Process Owner | If CSAT below 70% for 2 consecutive months: RCA + senior review
simplicityhub.co.uk |  |  | Control Plan ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html