## Blank Template
SH | SIMPLICITYHUB™ FISHBONE DIAGRAM |  |  |  | PRACTICAL TEMPLATE
Identify root causes across six key categories using a cause-and-effect structure. |  |  |  |  | FISHBONE DIAGRAM
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS FISHBONE DIAGRAM? | A Fishbone Diagram (Ishikawa / Cause-and-Effect Diagram) identifies potential causes of a problem across six categories: People/Man, Machine, Method/Process, Material, Measurement and Environment. Use it in the Analyse phase to organise root cause thinking before validation.
Problem / Effect
CAUSES BY CATEGORY |  |  | Enter causes identified for each of the six categories
Category | Cause 1 | Cause 2 | Cause 3 | Cause 4 | Cause 5
People / Man
Machine
Method / Process
Material
Measurement
Environment
simplicityhub.co.uk |  |  | Fishbone Diagram ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB™ FISHBONE DIAGRAM |  |  |  | PRACTICAL TEMPLATE
Identify root causes across six key categories using a cause-and-effect structure. |  |  |  |  | FISHBONE DIAGRAM
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS FISHBONE DIAGRAM? | A Fishbone Diagram (Ishikawa / Cause-and-Effect Diagram) identifies potential causes of a problem across six categories: People/Man, Machine, Method/Process, Material, Measurement and Environment. Use it in the Analyse phase to organise root cause thinking before validation.
Problem / Effect | Complaint response time exceeds 3-day SLA (current avg: 5.2 days)
CAUSES BY CATEGORY |  |  | Enter causes identified for each of the six categories
Category | Cause 1 | Cause 2 | Cause 3 | Cause 4 | Cause 5
People / Man | No standard investigation checklist | Agent training gaps — complaint handling | Role confusion — unclear authority levels | High staff turnover disrupts continuity
Machine | CRM not integrated with email channel | No real-time SLA alert or dashboard | Manual rekeying from online form | CRM system downtime (avg 2 hrs/wk)
Method / Process | No triage checklist or standard process | No closure script — inconsistent comms | No FCR target or measurement in place | Complaint process designed for speed, not quality
Material | No resolution toolkit for agents | Outdated policy documents in use | No FAQ or decision tree for common complaints | Missing escalation criteria document
Measurement | No real-time KPI dashboard | CSAT survey response rate only 34% | FCR flag inconsistently applied by agents | No early-warning metric for SLA risk
Environment | High volume: 47 complaints/day | Seasonal peaks not resourced | No priority system for urgent cases | Customers escalate directly to senior management
simplicityhub.co.uk |  |  | Fishbone Diagram ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Visual Fishbone
METHOD | MATERIAL | MACHINE
No triage checklist | No resolution toolkit for agents | CRM not integrated with email
No closure script | Outdated policy documents | No real-time SLA alerts
Process designed for speed, not quality | No FAQ / decision tree | CRM downtime (avg 2 hrs/wk)
PROBLEM / EFFECT Complaint response time exceeds 3‑day SLA (Current avg: 5.2 days)
Training gaps in complaint handling | High complaint volume (47/day) | No real-time KPI dashboard
Role confusion — unclear authority | Seasonal peaks not resourced | Low CSAT response rate
High staff turnover | No prioritisation for urgent cases | No SLA early warning metric
MANPOWER | ENVIRONMENT | MEASUREMENT