## Blank Template
SH | SIMPLICITYHUB® A3 PROBLEM SOLVING TEMPLATE |  |  |  |  | PRACTICAL TEMPLATE
For each problem, capture the background, current condition and goal, then log root causes, countermeasures and follow-up actions. The template keeps the whole A3 story on one page. |  |  |  |  | A3 PROBLEM SOLVING
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS AN A3 REPORT? | An A3 Report is a one-page problem-solving story that moves from background and problem statement through root cause analysis to countermeasures, an implementation plan and follow-up. It aligns the team and sponsor on a single sheet of paper, making thinking visible and progress easy to review.
A3 STORY |  |  | Complete each section in order. Keep each section short — the whole story must fit one page.
A3 Section | Your Content
COUNTERMEASURE LOG |  |  | One row per countermeasure with a named owner and date — the A3 is only as good as this table.
Countermeasure | Root Cause Addressed | Owner | Due Date | Status | Effect When Done
simplicityhub.co.uk |  |  | A3 PROBLEM SOLVING ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB® A3 PROBLEM SOLVING TEMPLATE |  |  |  |  | PRACTICAL TEMPLATE
For each problem, capture the background, current condition and goal, then log root causes, countermeasures and follow-up actions. The template keeps the whole A3 story on one page. |  |  |  |  | A3 PROBLEM SOLVING
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Sep 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS AN A3 REPORT? | An A3 Report is a one-page problem-solving story that moves from background and problem statement through root cause analysis to countermeasures, an implementation plan and follow-up. It aligns the team and sponsor on a single sheet of paper, making thinking visible and progress easy to review.
A3 STORY |  |  | Complete each section in order. Keep each section short — the whole story must fit one page.
A3 Section | Your Content
1. Background | Complaint responses were slow and inconsistent: 48-hour average first response, 14-day resolution, 17% escalation rate. Overtime £26k/year.
2. Current condition | 140-case backlog; each case read and typed free-hand; two approval steps; no milestone updates; customers chase by phone.
3. Goal / target condition | First response within 4 working hours; resolution within 10 days; escalation rate below 8%; backlog below 40 by 31 Oct 2026.
4. Root cause analysis | 5 Whys on the top 3 complaints: no triage checklist, no auto-acknowledgement, and unlinked approvals cause 78% of the delay.
5. Countermeasures | Triage checklist (08 Sep), CRM auto-acknowledgement (27 Sep), single approval below £50 (12 Sep), escalation matrix (12 Sep), daily stand-up (08 Sep).
6. Implementation plan | Training 10-24 Sep; checklist live 08 Sep; CRM change 27 Sep; go-live reviews at the daily stand-up; sponsor checkpoint fortnightly.
7. Follow-up / confirmation | KPI dashboard live 01 Oct; benefits tracker reviewed 08 Oct; response plan triggers daily on the board.
8. Lessons learned | Co-creating the checklist with agents halved training time; vendor API changes are the biggest schedule risk — book buffer.
COUNTERMEASURE LOG |  |  | One row per countermeasure with a named owner and date — the A3 is only as good as this table.
Countermeasure | Root Cause Addressed | Owner | Due Date | Status | Effect When Done
Triage checklist for 8 complaint types | No consistent case reading | Emma Clarke | 08 Sep 2026 | Live | Cut intake time 10 to 3 minutes
CRM auto-acknowledgement | Manual acknowledgement next day | David Osei | 27 Sep 2026 | In build | First response within minutes
Single approval below £50 | Duplicate approval flow | David Osei | 12 Sep 2026 | Signed off | 2-day approval cut to 5 minutes
Escalation matrix with response times | Unowned escalations | James Carter | 12 Sep 2026 | Live | Every escalation has a path
Daily 15-min stand-up | No early-warning routine | James Carter | 08 Sep 2026 | Live | Drift caught same-day
simplicityhub.co.uk |  |  | A3 PROBLEM SOLVING ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html