## Blank Template
SH | SIMPLICITYHUB™ AUDIT CHECKLIST |  |  |  | PRACTICAL TEMPLATE
Conduct a structured process audit — assess compliance, record evidence, findings and corrective actions. |  |  |  |  | AUDIT CHECKLIST
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS AUDIT CHECKLIST? | An Audit Checklist is used to conduct a structured review of whether the improved process is being followed as intended. For each item, record the category, the audit question or item, whether it is compliant (Yes/No/Partial/N/A), the evidence observed, any findings or gaps, the corrective action required, the owner and the due date. Use audit results to identify and address slippage early.
AUDIT FINDINGS REGISTER |  |  | Complete one row per audit item
Category | Audit Item | Compliant? | Evidence | Findings | Corrective Action | Owner | Due Date
simplicityhub.co.uk |  |  | Audit Checklist ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB™ AUDIT CHECKLIST |  |  |  | PRACTICAL TEMPLATE
Conduct a structured process audit — assess compliance, record evidence, findings and corrective actions. |  |  |  |  | AUDIT CHECKLIST
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS AUDIT CHECKLIST? | An Audit Checklist is used to conduct a structured review of whether the improved process is being followed as intended. For each item, record the category, the audit question or item, whether it is compliant (Yes/No/Partial/N/A), the evidence observed, any findings or gaps, the corrective action required, the owner and the due date. Use audit results to identify and address slippage early.
Items audited | 9 | Yes | 7 | No | 1 | Partial | 1 | Compliance % | 78%
AUDIT FINDINGS REGISTER |  |  | Complete one row per audit item
Category | Audit Item | Compliant? | Evidence | Findings | Corrective Action | Owner | Due Date
Process Compliance | Investigation checklist completed for 100% of sampled cases | Yes | 10/10 sampled cases had checklist fully completed | — | — | — | —
Process Compliance | Root cause coded at closure for 100% of sampled cases | Partial | 9/10 cases coded; 1 case missing root cause code | 1 agent did not apply root cause code — agent was absent on return from leave | Coach agent on return; re-audit this item next month | CS Team Lead | 01 May 2026
Controls | I-MR control chart reviewed weekly by process owner | Yes | Run chart reviewed w/e 05 Apr 2026 — no control signals identified | — | — | — | —
Controls | CRM SLA alert active and triggering correctly at 48-hour threshold | Yes | IT confirmed alert active; tested 07 Apr 2026 — alert fired correctly in 3/3 tests | — | — | — | —
Documentation | SOP CS-SOP-001 v1.0 accessible to all agents on intranet | Yes | Available on intranet; 3 agents asked to locate it and succeeded immediately | — | — | — | —
Documentation | Authority levels guide published and current (v1.0, Apr 2026) | Yes | Published 02 Apr 2026; confirmed accessible in CS Procedures folder | — | — | — | —
Training | All CS agents (12) have completed investigation checklist training | Yes | 12/12 agents on training register; all signed off on training record | — | — | — | —
Data & Reporting | CSAT survey trigger firing at correct point in process (24h post-closure) | No | Survey currently firing at 3-day resolution point, not 24h post-closure | Survey trigger timing not yet corrected — IT fix not yet deployed | IT to deploy trigger update by 28 Apr 2026 — confirmed in IT sprint | IT Lead | 28 Apr 2026
Data & Reporting | Monthly performance dashboard shared with stakeholders on schedule | Yes | Dashboard distributed to CS manager and sponsor 02 Apr 2026 | — | — | — | —
simplicityhub.co.uk |  |  | Audit Checklist ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html