## Blank Template
SH | SIMPLICITYHUB™ HANDOVER CHECKLIST |  |  |  | PRACTICAL TEMPLATE
Confirm all documentation, training, controls, data and communications are in place before handing over to the process owner. |  |  |  |  | HANDOVER CHECKLIST
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS HANDOVER CHECKLIST? | A Handover Checklist ensures that everything required to sustain the improved process has been put in place before the project team hands responsibility back to the process owner. Use this to confirm: documentation is complete and accessible; training has been delivered; controls are active; data and reporting is in place; technology changes are live; stakeholders have been communicated with; and ongoing actions have been assigned.
HANDOVER CHECKLIST ITEMS |  |  | Record status for each item — Complete, Not Complete or N/A
Category | Checklist Item | Status | Notes
simplicityhub.co.uk |  |  | Handover Checklist ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB™ HANDOVER CHECKLIST |  |  |  | PRACTICAL TEMPLATE
Confirm all documentation, training, controls, data and communications are in place before handing over to the process owner. |  |  |  |  | HANDOVER CHECKLIST
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS HANDOVER CHECKLIST? | A Handover Checklist ensures that everything required to sustain the improved process has been put in place before the project team hands responsibility back to the process owner. Use this to confirm: documentation is complete and accessible; training has been delivered; controls are active; data and reporting is in place; technology changes are live; stakeholders have been communicated with; and ongoing actions have been assigned.
Total items | 18 | Complete | 17 | Not Complete | 1 | % Ready | 94%
HANDOVER CHECKLIST ITEMS |  |  | Record status for each item — Complete, Not Complete or N/A
Category | Checklist Item | Status | Notes
Documentation | SOP (CS-SOP-001 v1.0) finalised and uploaded to intranet | Complete | Published 01 Apr 2026 — accessible to all CS agents
Documentation | Authority levels and escalation criteria guide distributed to team | Complete | Distributed 02 Apr 2026
Documentation | Standard closure communication script embedded in CS Procedures folder | Complete | v2 approved and uploaded 03 Apr 2026
Documentation | Control Plan reviewed and signed off by process owner | Complete | Signed off by James Carter 05 Apr 2026
Training | All 12 CS agents trained on investigation checklist | Complete | 100% attendance — training records filed
Training | Agent refresher training programme (closure script + authority levels) delivered | Complete | Delivered week of 21 Apr 2026
Training | Team Lead trained on CRM compliance reporting and reaction plan | Complete | Briefed 01 Apr 2026
Process & Controls | Investigation checklist embedded as mandatory field in CRM | Complete | Confirmed live and mandatory from 01 Apr 2026
Process & Controls | Root cause coding dropdown active as mandatory CRM field | Complete | Confirmed with IT — live from 01 Apr 2026
Process & Controls | CRM SLA alert triggering correctly at 48-hour threshold | Complete | IT confirmed active and tested 07 Apr 2026
Data & Reporting | Monthly performance dashboard template shared with CS manager and sponsor | Complete | Dashboard distributed 02 Apr 2026; schedule monthly
Data & Reporting | I-MR control chart for TTR set up and baselined | Complete | Chart set up by Process Owner; reviewed weekly
Data & Reporting | CSAT survey trigger timing fix deployed | Not Complete | IT to deploy by 28 Apr 2026 — in sprint
Technology | CRM-email integration project handed to IT with requirements document | Complete | Requirements signed off 07 Apr 2026
Stakeholder Comms | Project closure communicated to sponsor (Sarah Mitchell) | Complete | Closure presentation 18 Apr 2026
Stakeholder Comms | Benefits realisation review date agreed with sponsor | Complete | Agreed: 01 Jul 2026 (3-month post-implementation review)
Ongoing Actions | Monthly governance review scheduled with CS Team Lead | Complete | Monthly — first review 01 May 2026
Ongoing Actions | Annual SOP review date set | Complete | Review due 01 Apr 2027 — calendar invite sent
simplicityhub.co.uk |  |  | Handover Checklist ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html