## Blank Template
SH | SIMPLICITYHUB™ LESSONS LEARNED LOG |  |  |  | PRACTICAL TEMPLATE
Capture what went well, what didn't, why it happened and recommendations to improve future projects. |  |  |  |  | LESSONS LEARNED LOG
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS LESSONS LEARNED LOG? | A Lessons Learned Log captures the key learning points from a project — both positive and negative — so future project teams can build on what worked and avoid what didn't. For each lesson, record the category, DMAIC phase, what happened, the impact, the type (positive/negative/neutral), the root cause, the owner, and the recommendation for future projects.
LESSONS LEARNED REGISTER |  |  | Complete one row per lesson learned
Category | DMAIC Phase | Impact | What Happened | Type | Root Cause | Owner | Recommendation for Future Projects
simplicityhub.co.uk |  |  | Lessons Learned Log ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB™ LESSONS LEARNED LOG |  |  |  | PRACTICAL TEMPLATE
Capture what went well, what didn't, why it happened and recommendations to improve future projects. |  |  |  |  | LESSONS LEARNED LOG
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS LESSONS LEARNED LOG? | A Lessons Learned Log captures the key learning points from a project — both positive and negative — so future project teams can build on what worked and avoid what didn't. For each lesson, record the category, DMAIC phase, what happened, the impact, the type (positive/negative/neutral), the root cause, the owner, and the recommendation for future projects.
Total lessons | 8 | Positive | 4 | Negative | 4
LESSONS LEARNED REGISTER |  |  | Complete one row per lesson learned
Category | DMAIC Phase | Impact | What Happened | Type | Root Cause | Owner | Recommendation for Future Projects
Process | Improve | High | Involving front-line agents in checklist design drove significantly faster adoption than expected | Positive | Agents felt ownership of the change, not recipients of it | James Carter | Always co-design process tools with the people who will use them — budget time for co-design workshops
Measurement | Measure | High | CSAT response rate of 24% was too low to produce statistically reliable results during the Measure phase | Negative | Survey trigger fired too early in the resolution process — customers hadn't received full closure | Data Analyst | Validate measurement systems thoroughly before relying on data — fix CSAT trigger before Measure phase
Project Management | Define | Medium | Initial problem statement was too broad — needed to be narrowed before meaningful improvement work could begin | Negative | Insufficient VOC data at project start; scope set too wide by sponsor | James Carter | Invest more time in VOC and problem scoping — do not proceed to Measure until problem statement is agreed and signed off
Process | Analyse | High | Pareto analysis of root causes revealed 3 causes driving 76% of delays — gave very clear prioritisation immediately | Positive | Good quality baseline CRM data; well-structured data collection plan | James Carter | Always run Pareto analysis before solution selection — it removes debate and focuses the team
Technology | Improve | High | CRM integration project took approximately 3× longer than the original estimate due to IT resource constraints | Negative | IT resource allocation not confirmed before project plan was baselined | IT Lead | Get written confirmation of IT resource availability and commitment before including technology work in the project plan
People | Improve | Medium | Agent refresher training had 100% attendance and very positive feedback — scored 4.7/5 for usefulness | Positive | Good L&D brief, clear scheduling, training delivered during quieter period | L&D Lead | Schedule training during quieter periods — aim for minimum 2 weeks advance notice and secure line manager sign-off
Measurement | Improve | Medium | 2-week pilot period was insufficient to capture enough CSAT survey responses for statistical confidence | Negative | CSAT survey trigger not yet fixed when pilot ran — response rate remained low | James Carter | Fix measurement systems before running the pilot — do not run pilot until all data collection is validated
Project Management | Control | High | Weekly project reviews maintained team momentum and surfaced blockers early throughout the project | Positive | Clear agenda, pre-read discipline, and accountable owner for each action | Process Owner | Embed weekly reviews into the Control Plan — name an owner and set a standing calendar invite
simplicityhub.co.uk |  |  | Lessons Learned Log ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html