## Blank Template
SH | SIMPLICITYHUB™ PROJECT CLOSURE REPORT |  |  |  | PRACTICAL TEMPLATE
Formal project closure document — objectives vs results, financial summary, lessons learned, outstanding actions and sign-off. |  |  |  |  | PROJECT CLOSURE REPORT
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS PROJECT CLOSURE REPORT? | A Project Closure Report formally closes the project and summarises everything achieved. It covers: project details (dates, team); project summary; objectives vs results; financial summary (benefits and costs); what went well and could be improved; key lessons learned; outstanding actions and next steps; and formal sign-off by the project manager, sponsor and process owner.
PROJECT DETAILS
Planned Start Date
Planned End Date
Actual Closure Date
Project Manager
Sponsor
Department
TEAM MEMBERS
PROJECT SUMMARY — WHAT WAS DONE AND DELIVERED
OBJECTIVES AND RESULTS |  |  | How did actual results compare to targets?
Objective | Target | Result / Actual | Status
FINANCIAL SUMMARY
Target Annual Benefit
Realised Benefit (to date)
Benefit Notes
Projected Project Cost
Actual Project Cost
Cost Notes
WHAT WENT WELL
WHAT COULD BE IMPROVED
KEY LESSONS LEARNED — FOR FUTURE PROJECT TEAMS
OUTSTANDING ACTIONS (OWNER AND DUE DATE)
NEXT STEPS / PHASE 2
SIGN-OFF |  |  | Formal closure confirmation
Sign-Off — Names and Roles
Sign-Off Date
Sign-Off Notes
simplicityhub.co.uk |  |  | Project Closure Report ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB™ PROJECT CLOSURE REPORT |  |  |  | PRACTICAL TEMPLATE
Formal project closure document — objectives vs results, financial summary, lessons learned, outstanding actions and sign-off. |  |  |  |  | PROJECT CLOSURE REPORT
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS PROJECT CLOSURE REPORT? | A Project Closure Report formally closes the project and summarises everything achieved. It covers: project details (dates, team); project summary; objectives vs results; financial summary (benefits and costs); what went well and could be improved; key lessons learned; outstanding actions and next steps; and formal sign-off by the project manager, sponsor and process owner.
PROJECT DETAILS
Planned Start Date | 05 Jan 2026
Planned End Date | 28 Mar 2026
Actual Closure Date | 04 Apr 2026
Project Manager | James Carter
Sponsor | Sarah Mitchell
Department | Customer Service
TEAM MEMBERS
James Carter (Project Manager), Sarah Mitchell (Sponsor), CS Team Lead, Data Analyst, IT Lead, L&D Lead, Process Owner
PROJECT SUMMARY — WHAT WAS DONE AND DELIVERED
A Lean Six Sigma Improve project to reduce the average customer complaint response time from 5.2 days to ≤ 3.5 days and improve first contact resolution rate from 58% to ≥ 65%. The root causes identified were: absence of a structured investigation checklist; unclear agent authority levels; and no standard closure communication. Solutions delivered: mandatory investigation checklist in CRM; authority levels and escalation criteria guide; standard closure communication script; and refresher training for all 12 agents.
OBJECTIVES AND RESULTS |  |  | How did actual results compare to targets?
Objective | Target | Result / Actual | Status
Reduce average complaint response time (TTR) | ≤ 3.5 days | 3.8 days (post-pilot; continuing to improve) | Partially Achieved
Improve first contact resolution (FCR) rate | ≥ 65% | 62% — improving trend; not yet at target | Partially Achieved
Investigation checklist compliance | 100% | 97% (1 agent gap — coaching in progress) | Partially Achieved
CSAT score | ≥ 72% | 69% — improving from baseline of 67% | Partially Achieved
Control plan and SOP in place and live | By 01 Apr 2026 | Completed 01 Apr 2026 | Achieved
FINANCIAL SUMMARY
Target Annual Benefit | £180,000 per year (reduced repeat contacts, handling time reduction, agent efficiency)
Realised Benefit (to date) | Estimated £95,000 annualised in first month post-implementation (full realisation expected within 3 months as improvements bed in)
Benefit Notes | Benefits realisation review scheduled for 01 Jul 2026. Full annualised benefit expected once CSAT trigger is fixed and TTR stabilises below 3.5 days.
Projected Project Cost | £28,500 (project management time, training, CRM development, L&D resource)
Actual Project Cost | £31,200 (IT CRM integration took approximately 3× longer than estimated — additional IT resource required)
Cost Notes | Budget overrun driven by IT resource constraints not confirmed at project initiation. Lesson logged and recommendation to all future projects.
WHAT WENT WELL
Co-design of the investigation checklist with agents drove rapid adoption. Agent refresher training delivered with 100% attendance and scored 4.7/5. Pareto analysis provided rapid, clear prioritisation of root causes. Weekly project reviews maintained momentum and surfaced blockers early. Control plan and SOP delivered on schedule and signed off by process owner.
WHAT COULD BE IMPROVED
Problem statement scope was too broad at initiation — required narrowing before Measure phase could begin. CRM IT resource not confirmed before project plan was baselined — caused significant delay and cost overrun. CSAT survey trigger not fixed before the Measure phase — measurement data unreliable until late in the project. Pilot period was too short to capture statistical confidence on CSAT data.
KEY LESSONS LEARNED — FOR FUTURE PROJECT TEAMS
Always co-design process tools with the end users — it drives faster adoption. Confirm IT resource commitment in writing before including technology changes in the project plan. Fix measurement systems before relying on the data — do not start Measure with unvalidated data collection. Invest more time in VOC and problem scoping — do not proceed until the problem statement is agreed by sponsor.
OUTSTANDING ACTIONS (OWNER AND DUE DATE)
IT to deploy CSAT survey trigger fix by 28 Apr 2026 (owner: IT Lead). 1 agent to complete investigation checklist coaching session (owner: CS Team Lead, due: 12 Apr 2026). Monthly governance review established — first meeting 01 May 2026 (owner: CS Team Lead).
NEXT STEPS / PHASE 2
3-month benefits realisation review — 01 Jul 2026 (owner: James Carter, sponsor: Sarah Mitchell). If TTR and CSAT remain below target at Jul review: initiate Phase 2 — CRM email integration automation project. Annual SOP review — 01 Apr 2027 (owner: Process Owner).
SIGN-OFF |  |  | Formal closure confirmation
Sign-Off — Names and Roles | James Carter (Project Manager) · Sarah Mitchell (Sponsor) · CS Team Lead (Process Owner)
Sign-Off Date | 18 Apr 2026
Sign-Off Notes | Project formally closed. Control transferred to Process Owner. Benefits realisation review scheduled for 01 Jul 2026.
simplicityhub.co.uk |  |  | Project Closure Report ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html