## Blank Template
SH | SIMPLICITYHUB® PROJECT STATUS REPORT TEMPLATE |  |  |  |  | PRACTICAL TEMPLATE
For each milestone or deliverable, record percent complete, planned and forecast dates, then flag the RAG status with the risks. The template keeps reporting to one page. |  |  |  |  | PROJECT STATUS REPORT
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS A PROJECT STATUS REPORT? | A Project Status Report gives a sponsor the truth on one page — what is done, what is next, what is late and what is at risk. Milestones carry a percent complete and a forecast date, and the whole report carries one honest RAG status.
MILESTONES & DELIVERABLES |  |  | One line per milestone. Forecast date later than planned = a risk, not a surprise.
Milestone / Deliverable | Planned | Forecast | % Complete | RAG | Owner | Comment / Blocker | Next Step
RISKS & ISSUES LOG |  |  | Every red or amber milestone needs a line here with an owner and a mitigation.
Risk / Issue | Impact | Likelihood | Mitigation / Action | Owner | Status
simplicityhub.co.uk |  |  | PROJECT STATUS REPORT ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB® PROJECT STATUS REPORT TEMPLATE |  |  |  |  | PRACTICAL TEMPLATE
For each milestone or deliverable, record percent complete, planned and forecast dates, then flag the RAG status with the risks. The template keeps reporting to one page. |  |  |  |  | PROJECT STATUS REPORT
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Sep 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS A PROJECT STATUS REPORT? | A Project Status Report gives a sponsor the truth on one page — what is done, what is next, what is late and what is at risk. Milestones carry a percent complete and a forecast date, and the whole report carries one honest RAG status.
MILESTONES & DELIVERABLES |  |  | One line per milestone. Forecast date later than planned = a risk, not a surprise.
Milestone / Deliverable | Planned | Forecast | % Complete | RAG | Owner | Comment / Blocker | Next Step
SIPOC and process baseline | 05 Aug 2026 | 05 Aug 2026 | 100 | Green | James Carter | Complete | —
Root cause analysis complete | 22 Aug 2026 | 22 Aug 2026 | 100 | Green | James Carter | Five root causes confirmed | —
Checklist designed and signed off | 05 Sep 2026 | 05 Sep 2026 | 100 | Green | Emma Clarke | Live from 08 Sep | —
CRM auto-acknowledgement live | 20 Sep 2026 | 27 Sep 2026 | 60 | Amber | David Osei | Vendor API change request 3 days late | Chase vendor daily from 17 Sep
Agent training complete | 24 Sep 2026 | 24 Sep 2026 | 80 | Green | Emma Clarke | Two sessions remain | Final sessions 18 + 21 Sep
Escalation matrix agreed | 12 Sep 2026 | 12 Sep 2026 | 100 | Green | James Carter | Matrix live | —
KPI dashboard live to team | 01 Oct 2026 | 01 Oct 2026 | 40 | Green | Priya Nair | Build in progress | Demo 26 Sep
Benefits baseline signed off | 08 Oct 2026 | 08 Oct 2026 | 10 | Green | Sarah Mitchell | Scheduled | Kick-off 24 Sep
RISKS & ISSUES LOG |  |  | Every red or amber milestone needs a line here with an owner and a mitigation.
Risk / Issue | Impact | Likelihood | Mitigation / Action | Owner | Status
CRM vendor slips API change beyond 27 Sep | First-response benefit delayed 2 weeks | Medium | Daily chase; manual acknowledgement script as fallback | David Osei | Open
Peak-season volumes rise before benefits land | Backlog could re-grow in late Sep | High | Overtime cover approved 22-26 Sep | Sarah Mitchell | Open
Two agents on leave during training window | Uneven checklist adoption in week 1 | Medium | Catch-up session on return; buddy system | Emma Clarke | Closed
simplicityhub.co.uk |  |  | PROJECT STATUS REPORT ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html