## Blank Template
SH | SIMPLICITYHUB® RESPONSE PLAN TEMPLATE |  |  |  |  | PRACTICAL TEMPLATE
For each process measure, define the control limits and what triggers a reaction, then write the exact reaction and who owns it. The template makes the response automatic. |  |  |  |  | RESPONSE PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS A RESPONSE PLAN? | A Response Plan pre-decides what happens when a process measure drifts — the threshold that triggers action, the reaction required, who executes it and how the process returns to standard. Written before the drift, it removes judgement delays when the alarm fires.
RESPONSE PLAN |  |  | Every trigger needs an exact reaction with a named owner — "monitor" is not a response.
Measure | Trigger / Threshold | Reaction | Owner | Escalation If Repeated | Verification | Review Frequency
simplicityhub.co.uk |  |  | RESPONSE PLAN ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB® RESPONSE PLAN TEMPLATE |  |  |  |  | PRACTICAL TEMPLATE
For each process measure, define the control limits and what triggers a reaction, then write the exact reaction and who owns it. The template makes the response automatic. |  |  |  |  | RESPONSE PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Sep 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS A RESPONSE PLAN? | A Response Plan pre-decides what happens when a process measure drifts — the threshold that triggers action, the reaction required, who executes it and how the process returns to standard. Written before the drift, it removes judgement delays when the alarm fires.
RESPONSE PLAN |  |  | Every trigger needs an exact reaction with a named owner — "monitor" is not a response.
Measure | Trigger / Threshold | Reaction | Owner | Escalation If Repeated | Verification | Review Frequency
First-response time | Any day > 6 hours average | Same-day stand-up: assign oldest 10 cases to cover pair | Team leader | Service manager if 3 days in a row | Response log next morning | Daily
Backlog (open cases) | > 100 open cases | Stop non-urgent tasks; whole team on backlog until < 80 | Team leader | Service manager if breached twice in a week | Backlog count at stand-up | Daily
Checklist adoption | < 90% of cases in any day | Team leader reviews 5 skipped cases; re-coach at desk | Emma Clarke | Service manager if < 80% for a week | Adoption % next day | Weekly
Escalation rate | > 10% of cases escalated | Root-cause the day's escalations; check decision guide | James Carter | Head of Service if rising 2 weeks | Escalation log weekly | Weekly
Repeat contacts | > 12% chase within 7 days | Audit 10 chased cases; verify milestone updates ran | Priya Nair | Service manager if repeated | Chase-rate trend | Weekly
Decision consistency | < 92% like-for-like match | Re-brief resolution guide; double-check sample of 10 | James Carter | Head of Service if < 90% | Weekly consistency sample | Weekly
simplicityhub.co.uk |  |  | RESPONSE PLAN ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html