## Blank Template
SH | SIMPLICITYHUB™ SUSTAINABILITY PLAN |  |  |  | PRACTICAL TEMPLATE
Define how each improvement will be controlled and sustained long-term — with named owners, review frequency and escalation triggers. |  |  |  |  | SUSTAINABILITY PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS SUSTAINABILITY PLAN? | A Sustainability Plan defines how each improvement will be kept in place after the project closes. For each improvement, record the control measure (how it is maintained), the named owner, the review frequency, the escalation trigger (the condition under which it is escalated), the last and next review dates, and the current status. Review this plan regularly to confirm improvements are holding and to catch any slippage early.
SUSTAINABILITY REGISTER |  |  | Complete one row per improvement or control measure
Improvement | Control Measure | Owner | Review Frequency | Escalation Trigger | Last Review | Next Review | Status
simplicityhub.co.uk |  |  | Sustainability Plan ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB™ SUSTAINABILITY PLAN |  |  |  | PRACTICAL TEMPLATE
Define how each improvement will be controlled and sustained long-term — with named owners, review frequency and escalation triggers. |  |  |  |  | SUSTAINABILITY PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS SUSTAINABILITY PLAN? | A Sustainability Plan defines how each improvement will be kept in place after the project closes. For each improvement, record the control measure (how it is maintained), the named owner, the review frequency, the escalation trigger (the condition under which it is escalated), the last and next review dates, and the current status. Review this plan regularly to confirm improvements are holding and to catch any slippage early.
SUSTAINABILITY REGISTER |  |  | Complete one row per improvement or control measure
Improvement | Control Measure | Owner | Review Frequency | Escalation Trigger | Last Review | Next Review | Status
Investigation checklist compliance | Mandatory CRM field — case cannot be closed without completion. Weekly compliance report. | CS Team Lead | Weekly | Weekly completion rate drops below 95% — TL coaching + escalate to manager | 05 Apr 2026 | 12 Apr 2026 | On Track
Average response time (TTR) | I-MR control chart reviewed weekly by Process Owner. CRM SLA alert triggers at 48 hours. | Process Owner | Weekly | 3 consecutive points above UCL — RCA required; escalate to CS manager if unresolved in 1 week | 05 Apr 2026 | 12 Apr 2026 | On Track
Root cause coding | CRM mandatory field. Monthly audit sample of 30 cases reviewed by CS Team Lead. | CS Team Lead | Monthly | More than 5% uncoded in monthly audit — agent coaching session required within 5 days | 01 Apr 2026 | 01 May 2026 | On Track
CSAT score | Monthly CSAT run chart reviewed by Process Owner. Survey trigger fix deployed by 28 Apr. | Process Owner | Monthly | CSAT drops below 70% for 2 consecutive months — RCA and senior management review | 01 Apr 2026 | 01 May 2026 | On Track
Repeat contact rate | Monthly CRM report reviewed by CS Team Lead. Benchmarked against 30% target. | CS Team Lead | Monthly | Repeat contact rate exceeds 35% for 2 consecutive months — process review required | 01 Apr 2026 | 01 May 2026 | On Track
Agent refresher training | Annual training schedule maintained by L&D. Training records in HR system. | L&D Lead | Annual | Agent tenure >12 months since last training — schedule refresher within 4 weeks | 21 Apr 2026 | 21 Apr 2027 | On Track
CRM SLA alert and dashboard uptime | IT quarterly health check. Alert monitored daily — failure logged in IT incident system. | IT Lead | Quarterly | Dashboard or alert unavailable for >2 business days — IT escalation ticket raised | 07 Apr 2026 | 01 Jul 2026 | On Track
simplicityhub.co.uk |  |  | Sustainability Plan ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html