## Blank Template
SH | SIMPLICITYHUB™ BUSINESS CASE |  |  |  | PRACTICAL TEMPLATE
Present the rationale and evidence for investing in this project. |  |  |  |  | BUSINESS CASE
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS BUSINESS CASE? | A Business Case summarises why a project is worth doing. It presents the problem, the proposed solution, the expected costs and benefits, and a clear recommendation for decision-makers.
EXECUTIVE SUMMARY |  |  | One-paragraph overview for a busy decision-maker
Summarise the problem, solution, investment required and expected return...
CURRENT SITUATION |  |  | What is happening now and why does it matter?
Describe the current problem, baseline data and business impact...
PROPOSED SOLUTION |  |  | What will you do and how?
Describe the approach, team, timeline and key activities...
COST ANALYSIS |  |  | List all costs associated with delivering this project
Cost Item | One-off Cost | Annual Cost | Notes
BENEFIT ANALYSIS |  |  | List expected benefits — quantify where possible
Benefit |  | Annual Value | Type | Notes
RISK SUMMARY |  |  | Key risks and mitigations summary
Summarise top risks and how they will be managed...
RECOMMENDATION |  |  | What are you asking the sponsor to approve?
State clearly what decision you need and the next steps...
simplicityhub.co.uk |  |  | BUSINESS CASE ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB™ BUSINESS CASE |  |  |  | PRACTICAL TEMPLATE
Present the rationale and evidence for investing in this project. |  |  |  |  | BUSINESS CASE
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS BUSINESS CASE? | A Business Case summarises why a project is worth doing. It presents the problem, the proposed solution, the expected costs and benefits, and a clear recommendation for decision-makers.
EXECUTIVE SUMMARY |  |  | One-paragraph overview for a busy decision-maker
This business case recommends a 12-week process improvement project to reduce customer complaint response times from 5.2 days to the 3-day SLA target. An estimated project investment of £8,000 will generate annual savings of £24,000 in handling costs and protect an estimated £220,000 in at-risk revenue through improved CSAT and retention.
CURRENT SITUATION |  |  | What is happening now and why does it matter?
Since Q3 2025, the Customer Service team has consistently missed the 3-day complaint response SLA, averaging 5.2 days. This is generating £1,200 per day in repeat contact handling costs, holding CSAT at 67% against an 80% target, and driving a 23% escalation rate. The root cause is a fragmented complaint intake process with inconsistent logging, unclear ownership and no structured follow-up.
PROPOSED SOLUTION |  |  | What will you do and how?
Redesign the end-to-end complaint handling process using Lean improvement methods. This includes standardising intake triage, clarifying ownership at each handoff, configuring CRM tracking fields, building an agent quick-reference process guide, and introducing a structured follow-up workflow. Delivery in 12 weeks with a core team of 4.
COST ANALYSIS |  |  | List all costs associated with delivering this project
Cost Item | One-off Cost | Annual Cost | Notes
Project management time (3 days/wk × 12 weeks) | £7,200 | — | PM at £200/day — internal resource
Process redesign workshop (external facilitation) | £500 | — | One-day session with core team
CRM configuration and template updates | £300 | — | IT resource: 1.5 days at £200/day
Agent training materials and briefing time | £200 | — | Design and delivery: 0.5 day PM time
Contingency (10%) | £820 | — | 10% of total project cost
BENEFIT ANALYSIS |  |  | List expected benefits — quantify where possible
Benefit |  | Annual Value | Type | Notes
Reduction in repeat complaint handling |  | £18,000 | Cash | 15 repeat contacts eliminated per week × £23 handling cost
Reduced escalation management time |  | £6,240 | Cash | 2 hrs/wk director time saved at £60/hr
Improved customer retention (CSAT uplift) |  | £220,000 | Cash | 5% churn reduction on £4.4M annual revenue base
Reduced re-work and complaint duplication |  | £4,200 | Cash | 3 hrs/wk agent time saved at £15/hr across team of 6
Regulatory risk reduction |  | Non-cash | Non-cash | Lower escalation rate reduces exposure to formal complaints
RISK SUMMARY |  |  | Key risks and mitigations summary
Primary risks: agent resistance to process changes (mitigated by early engagement and clear communications) and CRM configuration delays (mitigated by IT lead in core team and sponsor escalation path). If unresolved, ROI could reduce by up to 30%.
RECOMMENDATION |  |  | What are you asking the sponsor to approve?
Proceed with the project as defined. Annual benefits exceed project costs by more than 30:1. Request sign-off from Operations Director by 07 Apr 2026 to allow project kick-off on 14 Apr 2026.
simplicityhub.co.uk |  |  | BUSINESS CASE ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html