## Blank Template
SH | SIMPLICITYHUB™ GOAL STATEMENT |  |  |  | PRACTICAL TEMPLATE
Set a measurable, time-bound target for your improvement project. |  |  |  |  | GOAL STATEMENT
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS GOAL STATEMENT? | A Goal Statement defines the measurable outcome of your improvement project. Using the SMART format, it sets a clear target, baseline, deadline and measure of success.
S | SPECIFIC — What PROCESS will be improved? |  | Be precise — name the process, not a theme
Type your answer here...
M | MEASURABLE — What METRIC will be tracked? |  | Choose one primary measure of success
Type your answer here...
M | MEASURABLE — FROM — current baseline |  | Current state — include source of data
Type your answer here...
A | ACHIEVABLE — TO — target state |  | The specific target — quantified and realistic
Type your answer here...
T | TIME-BOUND — BY WHEN? |  | A specific date, not 'ASAP'
Type your answer here...
M | MEASURABLE — HOW will it be MEASURED? |  | System, method, owner and frequency
Type your answer here...
S | SPECIFIC — What is EXCLUDED from this goal? |  | State what is out of scope to prevent drift
Type your answer here...
COMPLETED SMART GOAL STATEMENT
Write your completed SMART goal here. Format: "Reduce [metric] from [baseline] to [target] by [date], as measured by [method]."
simplicityhub.co.uk |  |  | GOAL STATEMENT ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB™ GOAL STATEMENT |  |  |  | PRACTICAL TEMPLATE
Set a measurable, time-bound target for your improvement project. |  |  |  |  | GOAL STATEMENT
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS GOAL STATEMENT? | A Goal Statement defines the measurable outcome of your improvement project. Using the SMART format, it sets a clear target, baseline, deadline and measure of success.
S | SPECIFIC — What PROCESS will be improved? |  | Be precise — name the process, not a theme
Customer complaint handling process
M | MEASURABLE — What METRIC will be tracked? |  | Choose one primary measure of success
Average complaint response time (days from receipt to resolution)
M | MEASURABLE — FROM — current baseline |  | Current state — include source of data
5.2 days (Q3 2025 average, CRM data)
A | ACHIEVABLE — TO — target state |  | The specific target — quantified and realistic
3.0 days or less — aligned to the published customer SLA target
T | TIME-BOUND — BY WHEN? |  | A specific date, not 'ASAP'
23 Jun 2026 (end of 12-week improvement project)
M | MEASURABLE — HOW will it be MEASURED? |  | System, method, owner and frequency
CRM system — average of (complaint closed date minus opened date), reported weekly by the team leader
S | SPECIFIC — What is EXCLUDED from this goal? |  | State what is out of scope to prevent drift
Complaint prevention initiatives; IT infrastructure investment; changes to staffing headcount
COMPLETED SMART GOAL STATEMENT
Reduce the average customer complaint response time from 5.2 days to 3.0 days or less by 23 Jun 2026, as measured by CRM closed-date minus opened-date reported weekly. This project excludes complaint prevention initiatives, IT infrastructure investment and staffing headcount decisions.
simplicityhub.co.uk |  |  | GOAL STATEMENT ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html