## Blank Template
SH | SIMPLICITYHUB™ PROJECT CHARTER |  |  |  | PRACTICAL TEMPLATE
Define your project purpose, scope, team and success criteria in one place. |  |  |  |  | PROJECT CHARTER
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS A PROJECT CHARTER? | A Project Charter formally authorises a project. It captures the problem, objective, scope, team and timeline — giving everyone a shared understanding before work begins.
PROBLEM STATEMENT |  |  | What issue are we solving and why does it matter?
Describe the problem this project is addressing...
PROJECT OBJECTIVE |  |  | What does success look like? Be specific and measurable.
State the objective using measurable targets where possible...
BUSINESS CASE |  |  | Why is this project worth doing now?
Summarise the financial, operational or strategic benefit...
PROJECT SCOPE |  |  | What is and is not included in this project
IN SCOPE |  |  | OUT OF SCOPE
PROJECT TEAM
NAME |  | ROLE |  | DEPARTMENT
KEY MILESTONES
MILESTONE |  |  | TARGET DATE |  | OWNER
RISKS & CONSTRAINTS |  |  | Key risks, assumptions and project constraints
List key risks with mitigations, and any constraints that may affect delivery...
NOTES & ASSUMPTIONS |  |  | Any additional context or working assumptions
simplicityhub.co.uk |  |  | Project Charter ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB™ PROJECT CHARTER |  |  |  | PRACTICAL TEMPLATE
Define your project purpose, scope, team and success criteria in one place. |  |  |  |  | PROJECT CHARTER
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS A PROJECT CHARTER? | A Project Charter formally authorises a project. It captures the problem, objective, scope, team and timeline — giving everyone a shared understanding before work begins.
PROBLEM STATEMENT |  |  | What issue are we solving and why does it matter?
Customer complaint response times are averaging 5.2 days, exceeding our 3-day SLA target. This is resulting in repeat contacts, declining CSAT scores (currently 67%) and avoidable escalations to senior management. If left unaddressed, this will continue to increase operational cost and risk customer churn.
PROJECT OBJECTIVE |  |  | What does success look like? Be specific and measurable.
Reduce average complaint response time from 5.2 days to 3 days within 12 weeks. Improve CSAT from 67% to 80% by improving first-contact resolution and reducing repeat contacts by 30%.
BUSINESS CASE |  |  | Why is this project worth doing now?
Each day over SLA costs approximately £1,200 in repeat handling and escalation effort. Resolving this will reduce operational cost by approximately £18,000 annually. Improved CSAT is expected to reduce customer churn by 5%, protecting approximately £220,000 in annual revenue.
PROJECT SCOPE |  |  | What is and is not included in this project
IN SCOPE |  |  | OUT OF SCOPE
Complaint intake via phone, email and online form |  |  | Complaint prevention and root cause elimination
CRM logging and categorisation process |  |  | IT infrastructure upgrades or system replacements
SLA monitoring and escalation routing |  |  | Staff recruitment or headcount decisions
Agent response workflows and templates |  |  | Supplier and third-party complaint processes
Complaint trend reporting and dashboards |  |  | Customer satisfaction survey design
PROJECT TEAM
NAME |  | ROLE |  | DEPARTMENT
James Carter |  | Project Owner |  | Operations
Sarah Ahmed |  | Process Analyst |  | Customer Service
Tom Barker |  | IT Lead |  | Systems & Technology
Louise Chen |  | QA Manager |  | Quality
Sarah Mitchell |  | Executive Sponsor |  | Director Level
KEY MILESTONES
MILESTONE |  |  | TARGET DATE |  | OWNER
Define current state and baseline metrics |  |  | 14 Apr 2026 |  | James Carter
Root cause analysis and stakeholder review |  |  | 28 Apr 2026 |  | Sarah Ahmed
Solution design and approval |  |  | 12 May 2026 |  | Team
Pilot implementation and testing |  |  | 02 Jun 2026 |  | Tom Barker
Full rollout and project closure |  |  | 23 Jun 2026 |  | James Carter
RISKS & CONSTRAINTS |  |  | Key risks, assumptions and project constraints
Risk 1 — CRM system limitations may slow logging improvements. Mitigation: involve IT lead from week 1 and assess workarounds early. Risk 2 — Agent resistance to process change. Mitigation: involve team leads in solution design and communicate benefits clearly. Constraint: Project must be delivered within existing headcount — no additional resource approved.
NOTES & ASSUMPTIONS |  |  | Any additional context or working assumptions
Project approved by Operations Director on 28 Mar 2026. Budget confirmed at £8,000 for process redesign and tooling adjustments. This charter to be reviewed at the end of week 4 if scope assumptions change.
simplicityhub.co.uk |  |  | Project Charter ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html