## Blank Template
SH | SIMPLICITYHUB™ PROJECT RISK ASSESSMENT |  |  |  | PRACTICAL TEMPLATE
Identify risks early and plan mitigations to protect delivery. |  |  |  |  | PROJECT RISK ASSESSMENT
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS PROJECT RISK ASSESSMENT? | A Risk Assessment identifies potential problems before they happen. By rating each risk on likelihood and impact, you can prioritise your mitigations and protect project delivery.
Risk Score = Likelihood (1–5) × Impact (1–5) ¦ 1–4: Low ¦ 5–9: Medium ¦ 10–16: High ¦ 17–25: Critical
# | Risk Description | Category | L × I | Score | Mitigation / Owner / Status
1 |  |  | — | —
2 |  |  | — | —
3 |  |  | — | —
4 |  |  | — | —
5 |  |  | — | —
6 |  |  | — | —
7 |  |  | — | —
8 |  |  | — | —
9 |  |  | — | —
10 |  |  | — | —
simplicityhub.co.uk |  |  | PROJECT RISK ASSESSMENT ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB™ PROJECT RISK ASSESSMENT |  |  |  | PRACTICAL TEMPLATE
Identify risks early and plan mitigations to protect delivery. |  |  |  |  | PROJECT RISK ASSESSMENT
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS PROJECT RISK ASSESSMENT? | A Risk Assessment identifies potential problems before they happen. By rating each risk on likelihood and impact, you can prioritise your mitigations and protect project delivery.
Risk Score = Likelihood (1–5) × Impact (1–5) ¦ 1–4: Low ¦ 5–9: Medium ¦ 10–16: High ¦ 17–25: Critical
# | Risk Description | Category | L × I | Score | Mitigation / Owner / Status
1 | CRM system cannot support new complaint logging requirements | Technical | 3 × 4 | 12 | Assess CRM capability in week 1; identify workaround or alternative approach if needed ¦ Owner: Tom Barker ¦ Status: Open
2 | Agent resistance to new complaint process and ways of working | People | 3 × 3 | 9 | Involve team leads in process design; run change communications early and throughout project ¦ Owner: Sarah Ahmed ¦ Status: Open
3 | Key project team member unavailable during delivery | Resource | 2 × 4 | 8 | Cross-train on all workstreams; document decisions and design choices as project progresses ¦ Owner: James Carter ¦ Status: Open
4 | Scope creep — additional requirements added during project | Process | 3 × 3 | 9 | Strict change control in place; all scope changes must be approved by sponsor before actioning ¦ Owner: James Carter ¦ Status: Open
5 | Process changes worsen performance in short term during transition | Process | 2 × 3 | 6 | Monitor daily KPIs in first 2 weeks of pilot; rollback plan agreed with team before go-live ¦ Owner: Sarah Ahmed ¦ Status: Open
6 | Finance approval for project budget delayed beyond week 2 | Resource | 2 × 3 | 6 | Early engagement with finance; pre-agreed budget envelope submitted in advance of start date ¦ Owner: James Carter ¦ Status: Open
7 | Complaint volumes increase significantly during the project period | External | 2 × 2 | 4 | Project will not reduce available capacity; monitor weekly and flag to sponsor if volumes spike ¦ Owner: James Carter ¦ Status: Monitor
8 | Legal review required for changes to complaint process documentation | Compliance | 1 × 4 | 4 | Flag all process changes to compliance team for sign-off before any rollout is approved ¦ Owner: Louise Chen ¦ Status: Open
9 | IT changes delayed due to competing business priorities | Technical | 3 × 3 | 9 | IT lead embedded in core team; sponsor escalation path available if IT resource is blocked ¦ Owner: Tom Barker ¦ Status: Open
10 | Pilot site unavailable or unsuitable for testing new process | Resource | 1 × 2 | 2 | Identify 2 potential pilot sites and confirm availability by end of week 3 of the project ¦ Owner: Sarah Ahmed ¦ Status: Open
simplicityhub.co.uk |  |  | PROJECT RISK ASSESSMENT ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html