## Blank Template
SH | SIMPLICITYHUB® TEAM CHARTER TEMPLATE |  |  |  |  | PRACTICAL TEMPLATE
Agree the purpose, scope and ground rules with the team and sponsor before the work starts. The template records the deal everyone signed up to. |  |  |  |  | TEAM CHARTER
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS A TEAM CHARTER? | A Team Charter is the working agreement between a project team and its sponsor — why the team exists, what is in and out of scope, who does what, how decisions get made and how the team behaves. Written down and agreed up front, it prevents drift and dispute later.
TEAM CHARTER |  |  | Every field needs real agreement — a charter the team has not discussed is a poster, not a charter.
Field | Content
simplicityhub.co.uk |  |  | TEAM CHARTER ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB® TEAM CHARTER TEMPLATE |  |  |  |  | PRACTICAL TEMPLATE
Agree the purpose, scope and ground rules with the team and sponsor before the work starts. The template records the deal everyone signed up to. |  |  |  |  | TEAM CHARTER
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Sep 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS A TEAM CHARTER? | A Team Charter is the working agreement between a project team and its sponsor — why the team exists, what is in and out of scope, who does what, how decisions get made and how the team behaves. Written down and agreed up front, it prevents drift and dispute later.
TEAM CHARTER |  |  | Every field needs real agreement — a charter the team has not discussed is a poster, not a charter.
Field | Content
Team name | Complaint Response Improvement Team
Purpose | Cut first-response time from 48 hours to 4 hours and reduce repeat contacts by half
Scope — in | All written complaints across web form, email and letter; intake to verified closure
Scope — out | Phone complaints (separate queue); new product complaints; legal escalations
Business case | £26k/year overtime + churn risk from slow responses; CSSC-aligned service standard
Members & roles | James Carter — lead; Emma Clarke — process owner; Priya Nair — comms; David Osei — CRM/systems; Team leader — front line
Sponsor | Sarah Mitchell, Head of Service — monthly review, removes blockers
Ground rules | Decisions by consent, not volume; one conversation at a time; issues raised within 24 hours; stand-up daily 09:00
Milestones | Checklist live 08 Sep; CRM auto-acknowledgement 27 Sep; benefits review 08 Oct
Duration & review | Runs to 31 Oct 2026; fortnightly sponsor checkpoint; charter revisited at each checkpoint
simplicityhub.co.uk |  |  | TEAM CHARTER ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html