## Blank Template
SH | SIMPLICITYHUB™ CHANGE IMPLEMENTATION PLAN |  |  |  | PRACTICAL TEMPLATE
Track workstreams, change activities, owners, dates, RAG status and completion. |  |  |  |  | CHANGE IMPLEMENTATION PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS CHANGE IMPLEMENTATION PLAN? | A Change Implementation Plan organises all activities needed to deploy the solution into workstreams. For each activity, record the key implementation steps, owner, planned start and end dates, dependencies, RAG status and completion status. Review weekly to maintain momentum and surface blockers early.
RAG STATUS GUIDE |  |  | Green = on track · Amber = at risk — action required · Red = off track — escalation required · Blue = complete · Grey = not started
CHANGE ACTIVITY REGISTER |  |  | Organised by workstream
Workstream | Change Activity | Key Steps | Owner | Start Date | End Date | Dependencies | RAG | Status | Notes
simplicityhub.co.uk |  |  | Change Implementation Plan ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB™ CHANGE IMPLEMENTATION PLAN |  |  |  | PRACTICAL TEMPLATE
Track workstreams, change activities, owners, dates, RAG status and completion. |  |  |  |  | CHANGE IMPLEMENTATION PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS CHANGE IMPLEMENTATION PLAN? | A Change Implementation Plan organises all activities needed to deploy the solution into workstreams. For each activity, record the key implementation steps, owner, planned start and end dates, dependencies, RAG status and completion status. Review weekly to maintain momentum and surface blockers early.
RAG STATUS GUIDE |  |  | Green = on track · Amber = at risk — action required · Red = off track — escalation required · Blue = complete · Grey = not started
CHANGE ACTIVITY REGISTER |  |  | Organised by workstream
Workstream | Change Activity | Key Steps | Owner | Start Date | End Date | Dependencies | RAG | Status | Notes
Process | Implement investigation checklist in CRM | Agree checklist fields; CRM config; agent briefing; pilot | James Carter | 28 Mar 2026 | 14 Apr 2026 | — | Green | In Progress | Pilot underway w/c 01 Apr
Process | Redesign closure process — root cause coding | Process redesign; CRM closure screen update; training | James Carter | 04 Apr 2026 | 21 Apr 2026 | 1 | Amber | Not Started | Awaiting checklist sign-off
Communication | Develop and embed standard closure script | Draft script; TL review; embed in process; training | Sarah Ahmed | 28 Mar 2026 | 10 Apr 2026 | — | Green | In Progress | Draft v2 with TLs
People | Publish authority levels and escalation criteria | Draft levels; TL review; approval; publish; training update | James Carter | 01 Apr 2026 | 04 Apr 2026 | — | Green | Complete | Distributed 02 Apr 2026
Technology | SLA alert and real-time dashboard in CRM | IT scoping; build; UAT; go-live | IT Lead | 07 Apr 2026 | 30 Apr 2026 | — | Amber | Not Started | IT sprint planning w/c 07 Apr
Technology | CRM-email channel integration project | Business requirements; IT build; test; go-live | IT Lead | 07 Apr 2026 | 30 May 2026 | — | Amber | In Progress | Discovery phase underway
People | Agent refresher training programme | L&D brief; content build; schedule; deliver | L&D Lead | 14 Apr 2026 | 21 Apr 2026 | 1, 3 | Red | Not Started | L&D brief submitted 02 Apr
Measurement | CSAT survey trigger timing and survey fix | IT config change; test; deploy | IT Lead | 21 Apr 2026 | 28 Apr 2026 | 6 | Amber | Not Started | Depends on CRM integration
simplicityhub.co.uk |  |  | Change Implementation Plan ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html