## Blank Template
SH | SIMPLICITYHUB™ RISK MITIGATION PLAN |  |  |  | PRACTICAL TEMPLATE
Identify, score and mitigate risks that could affect the success of the improvement project. |  |  |  |  | RISK MITIGATION PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS RISK MITIGATION PLAN? | A Risk Mitigation Plan documents each risk, scores it by likelihood (1–5) and impact (1–5), calculates the risk score (L × I, max 25) and defines a mitigation action to reduce the risk and a contingency plan in case the risk materialises. Review regularly throughout the project.
RISK SCORE GUIDE (L × I) |  |  | 1–2 Very Low · 3–5 Low · 6–11 Medium · 12–19 High · 20–25 Critical
RISK REGISTER |  |  | Score Likelihood and Impact 1 (very unlikely / minor) → 5 (very likely / severe)
Risk | Category | L (1–5) | I (1–5) | Score | Mitigation | Contingency | Owner | Target Date | Residual | Status
simplicityhub.co.uk |  |  | Risk Mitigation Plan ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB™ RISK MITIGATION PLAN |  |  |  | PRACTICAL TEMPLATE
Identify, score and mitigate risks that could affect the success of the improvement project. |  |  |  |  | RISK MITIGATION PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS RISK MITIGATION PLAN? | A Risk Mitigation Plan documents each risk, scores it by likelihood (1–5) and impact (1–5), calculates the risk score (L × I, max 25) and defines a mitigation action to reduce the risk and a contingency plan in case the risk materialises. Review regularly throughout the project.
RISK SCORE GUIDE (L × I) |  |  | 1–2 Very Low · 3–5 Low · 6–11 Medium · 12–19 High · 20–25 Critical
RISK REGISTER |  |  | Score Likelihood and Impact 1 (very unlikely / minor) → 5 (very likely / severe)
Risk | Category | L (1–5) | I (1–5) | Score | Mitigation | Contingency | Owner | Target Date | Residual | Status
Pilot fails to achieve KPI targets | Process | 2 | 4 | 8 Medium | Pilot design checklist; pre-pilot agent briefing; daily monitoring | Revert to current process; investigate root cause of pilot failure | James Carter | 14 Apr 2026 | Medium | Active
CRM integration project exceeds budget or timeline | Technology | 3 | 4 | 12 High | Detailed IT scoping; resource sign-off before start | Prioritise interim email workflow; escalate to Sarah Mitchell | IT Lead | 30 Apr 2026 | Medium | Active
Agent resistance to new investigation process | People | 2 | 3 | 6 Medium | Involve agents in checklist design; communicate rationale; share early quick wins | Investigate concerns; adjust process based on feedback | James Carter | 07 Apr 2026 | Low | Active
Low CSAT survey response rate continues to distort data | Measurement | 3 | 3 | 9 Medium | Survey trigger fix and timing change; target 50% response rate | Accept lower sample during transition; review monthly | IT Lead | 28 Apr 2026 | Low | Active
Project scope creep — additional change requests added | Project | 3 | 3 | 9 Medium | Change control process; scope document signed off by sponsor | Defer out-of-scope items to Phase 2; escalate to sponsor | James Carter | Ongoing | Low | Active
simplicityhub.co.uk |  |  | Risk Mitigation Plan ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html