## Change Readiness Checklist
SimplicityHub™ — Change Readiness Checklist
Check whether the team, process and environment are ready before implementing a change.
Stage: Improve ¦ Level: Beginner ¦ Best for: Avoiding surprises on go-live day by thinking through readiness in advance.
Readiness Area | Question | Yes / No / Partial | Action Needed | Owner | Due Date
Training | Has everyone been trained on the new process? | Partial | Run session for night shift | L. Harris | 14/04/2026
Communication | Do all affected staff know the change is happening? | Yes | None | - | -
Equipment | Is all equipment tested and in place? | No | Order 2 additional scanners | M. Patel | 12/04/2026
Documentation | Are updated work instructions available? | Partial | Finish v2 of SOP | K. Jones | 13/04/2026
Sign-off | Has the process owner approved go-live? | No | Schedule review meeting | Project Lead | 11/04/2026
Contingency | Is there a rollback plan if it does not work? | Yes | Documented in project file | - | -
© 2026 SimplicityHub™ — Free template. Visit simplicityhub.co.uk for more resources.