## Blank Template
SH | SIMPLICITYHUB® CHANGE MANAGEMENT PLAN TEMPLATE |  |  |  |  | PRACTICAL TEMPLATE
For each stakeholder group, capture the current and desired state, the actions and comms that move them, and the resistance risk. The template assigns an owner to every move. |  |  |  |  | CHANGE MANAGEMENT
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS A CHANGE MANAGEMENT PLAN? | A Change Management Plan sets out how the people side of an improvement will be delivered — who is affected, what changes for them, how they will be supported and communicated with, and how resistance will be spotted and handled. It protects the gains a project makes by making them stick.
STAKEHOLDER CHANGE LOG |  |  | Score resistance risk High/Medium/Low and revisit it at every review.
Stakeholder Group | Current State | Desired State | Change Actions | Communication Method | Owner | Timeline | Resistance Risk | Success Signal
simplicityhub.co.uk |  |  | CHANGE MANAGEMENT PLAN ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB® CHANGE MANAGEMENT PLAN TEMPLATE |  |  |  |  | PRACTICAL TEMPLATE
For each stakeholder group, capture the current and desired state, the actions and comms that move them, and the resistance risk. The template assigns an owner to every move. |  |  |  |  | CHANGE MANAGEMENT
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Sep 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS A CHANGE MANAGEMENT PLAN? | A Change Management Plan sets out how the people side of an improvement will be delivered — who is affected, what changes for them, how they will be supported and communicated with, and how resistance will be spotted and handled. It protects the gains a project makes by making them stick.
STAKEHOLDER CHANGE LOG |  |  | Score resistance risk High/Medium/Low and revisit it at every review.
Stakeholder Group | Current State | Desired State | Change Actions | Communication Method | Owner | Timeline | Resistance Risk | Success Signal
Complaint handlers (12) | Working cases from one shared inbox, free-text replies | Use triage checklist and templates; focus time on complex cases | Training workshop 10 Sep; desk-side coaching week 1-2; quick-reference card at desk | Team briefing + coaching + printed guide | Emma Clarke | 10-24 Sep 2026 | Medium — new steps seen as extra work | Checklist used on 95% of cases without prompts
Team leaders (3) | Review each case individually | Run daily 15-min stand-up on the KPI board | Brief leaders 08 Sep; shadow stand-ups week 1; hand over board ownership | 1:1 briefing + shadowing | James Carter | 08-30 Sep 2026 | Low — already supportive | Stand-ups run without agent prompting
Finance (2) | Manual overtime claim rework each month | Read standard report; no rework needed | Walk through new report 15 Sep; agree month-end cut-off | Email + 30-min walkthrough | David Osei | 15-30 Sep 2026 | Medium — trust in new report | Report accepted first month without rework
Customers | Chase for updates after 2 days | Receive acknowledgement within 4 hours | Launch auto-acknowledgement 20 Sep; update complaint leaflet | Automated email + website note | Priya Nair | 20 Sep 2026 | Low | First-response complaints fall below 5/month
Senior sponsor | Monthly verbal update | One-page A3 at monthly review | Agree A3 format 05 Sep | Monthly review meeting | Sarah Mitchell | From 05 Sep | Low | Signed-off A3 at each review
simplicityhub.co.uk |  |  | CHANGE MANAGEMENT PLAN ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html