## Blank Template
SH | SIMPLICITYHUB® SOLUTION SELECTION MATRIX TEMPLATE |  |  |  |  | PRACTICAL TEMPLATE
Score each solution against the criteria — impact, cost, time, risk, effort — on the same 1-5 scale, then total and compare. The template shows the winner and the trade-offs. |  |  |  |  | SOLUTION SELECTION
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS A SOLUTION SELECTION MATRIX? | A Solution Selection Matrix scores candidate solutions against agreed criteria on a common scale, so the team chooses on evidence rather than volume. Impact and cost carry the most weight in discussion, and the totals make the trade-offs visible before anyone commits.
SOLUTION SCORING |  |  | Score 1 (poor) to 5 (excellent) per criterion. Impact 5 = solves the root cause completely.
Solution | Impact | Cost (5 = low) | Time (5 = fast) | Risk (5 = low) | Effort (5 = low) | Total | Selected | Notes
simplicityhub.co.uk |  |  | SOLUTION SELECTION MATRIX ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB® SOLUTION SELECTION MATRIX TEMPLATE |  |  |  |  | PRACTICAL TEMPLATE
Score each solution against the criteria — impact, cost, time, risk, effort — on the same 1-5 scale, then total and compare. The template shows the winner and the trade-offs. |  |  |  |  | SOLUTION SELECTION
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Sep 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS A SOLUTION SELECTION MATRIX? | A Solution Selection Matrix scores candidate solutions against agreed criteria on a common scale, so the team chooses on evidence rather than volume. Impact and cost carry the most weight in discussion, and the totals make the trade-offs visible before anyone commits.
SOLUTION SCORING |  |  | Score 1 (poor) to 5 (excellent) per criterion. Impact 5 = solves the root cause completely.
Solution | Impact | Cost (5 = low) | Time (5 = fast) | Risk (5 = low) | Effort (5 = low) | Total | Selected | Notes
Triage checklist for every complaint | 5 | 5 | 5 | 4 | 5 | 24 | YES | Team co-created; live 08 Sep
Auto-acknowledgement in CRM | 4 | 4 | 3 | 4 | 3 | 18 | YES | Live 27 Sep with checklist
Chatbot for status questions | 2 | 2 | 2 | 3 | 2 | 11 | No | Park — revisit after checklist settles
Hire two extra agents | 3 | 1 | 1 | 3 | 1 | 9 | No | Cost and lead time rule it out
Escalation matrix with response times | 4 | 5 | 5 | 5 | 4 | 23 | YES | Agreed 12 Sep
Address lookup with postcode validation | 2 | 3 | 4 | 4 | 3 | 16 | No | Schedule next quarter
Daily 15-min stand-up on KPI board | 3 | 5 | 5 | 5 | 5 | 23 | YES | Live from 08 Sep
simplicityhub.co.uk |  |  | SOLUTION SELECTION MATRIX ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html