## Blank Template
SH | SIMPLICITYHUB™ SOLUTION TESTING PLAN |  |  |  | PRACTICAL TEMPLATE
Define test cases with acceptance criteria, methods, data requirements, owners and results. |  |  |  |  | SOLUTION TESTING PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS SOLUTION TESTING PLAN? | A Solution Testing Plan documents every test needed to validate the solution before full-scale implementation. For each test case, define what is being tested, the acceptance criteria (the definition of pass), the test method, data required, owner and planned date. Record the result and outcome once the test has been run.
Total | 0 | Pass | 0 | Fail | 0 | Pending | 0
TEST CASE REGISTER |  |  | Document, assign and track each test case through to result
Test ID | Test Name | What Is Being Tested | Acceptance Criteria | Test Method | Data Required | Owner | Planned Date | Result | Outcome / Observations | Notes
simplicityhub.co.uk |  |  | Solution Testing Plan ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB™ SOLUTION TESTING PLAN |  |  |  | PRACTICAL TEMPLATE
Define test cases with acceptance criteria, methods, data requirements, owners and results. |  |  |  |  | SOLUTION TESTING PLAN
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS SOLUTION TESTING PLAN? | A Solution Testing Plan documents every test needed to validate the solution before full-scale implementation. For each test case, define what is being tested, the acceptance criteria (the definition of pass), the test method, data required, owner and planned date. Record the result and outcome once the test has been run.
Total | 8 | Pass | 2 | Fail | 0 | Pending | 6
TEST CASE REGISTER |  |  | Document, assign and track each test case through to result
Test ID | Test Name | What Is Being Tested | Acceptance Criteria | Test Method | Data Required | Owner | Planned Date | Result | Outcome / Observations | Notes
TC-01 | Checklist Usability Test | Investigation checklist can be completed by an agent within 2 minutes unaided | Avg completion time ≤ 2 minutes; agent usability rating ≥ 4/5 | Timed observation with 3 agents; feedback survey | Draft checklist; 3 test complaints | James Carter | 01 Apr 2026 | Pass | Avg 1.6 min; minor label edits made | Passed with minor edits
TC-02 | CRM Checklist Integration UAT | Checklist fields save correctly in CRM case record and appear in case history | 100% of test cases save all checklist fields without error | End-to-end UAT in CRM test environment (10 cases) | CRM test environment; test case list | IT Lead | 05 Apr 2026 | Pending | — | Pending IT build
TC-03 | SLA Alert — Trigger Accuracy | SLA alert fires within 15 minutes of a case reaching the 48-hour breach threshold | 100% trigger accuracy across 20 test cases; no false positives | Create test cases; time alert trigger in CRM test environment | CRM test environment | IT Lead | 08 Apr 2026 | Pending | — | Pending IT build
TC-04 | Closure Script — Customer Response | Customers rate communication ≥ 4/5 when the standard closure script is used | Post-call survey rating ≥ 4/5 for ≥ 80% of test calls | Mystery shop (6 calls); post-call survey | Agent script; mystery shopper; survey form | Sarah Ahmed | 10 Apr 2026 | Pending | — | Awaiting script sign-off
TC-05 | Pilot — Response Time | Pilot group achieves average complaint response time ≤ 3.5 days over 2-week pilot | Avg response time ≤ 3.5 days (current baseline: 5.2 days) | 2-week controlled pilot; data extracted from CRM | Pilot group live cases (Team A) | James Carter | 14 Apr 2026 | Pending | — | Pilot 01–14 Apr
TC-06 | Pilot — Repeat Contact Rate | Pilot group repeat contact rate drops to ≤ 30% during the pilot period | Repeat contact rate ≤ 30% (current baseline: 38%) | 2-week pilot; CRM repeat contact flag analysis | Same live cases as TC-05 | James Carter | 14 Apr 2026 | Pending | — | Pilot 01–14 Apr
TC-07 | Pilot — CSAT Score | Pilot group CSAT score improves to ≥ 72% during the pilot period | CSAT score ≥ 72% (current baseline: 67%) | Post-resolution CSAT survey data (pilot period) | CSAT survey data; pilot period filter | Data Analyst | 14 Apr 2026 | Pending | — | Pending pilot completion
TC-08 | Authority Guide — Knowledge Check | 90% of agents correctly identify their resolution authority for 5 test scenarios | ≥ 90% of agents score ≥ 4/5 on knowledge check | Written knowledge check (5 scenarios) | Authority guide; knowledge check form | James Carter | 05 Apr 2026 | Pass | 11/12 agents 5/5; 1 agent 4/5 | Passed — 92%
simplicityhub.co.uk |  |  | Solution Testing Plan ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html