## Blank Template
SH | SIMPLICITYHUB™ DAILY MANAGEMENT BOARD |  |  |  | PRACTICAL TEMPLATE
Structure your daily team standup — review SQDCP performance, surface issues, assign actions and set today's priorities. |  |  |  |  | DAILY MANAGEMENT BOARD
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS DAILY MANAGEMENT BOARD? | A Daily Management Board structures the daily team standup meeting, ensuring consistent review of Safety, Quality, Delivery, Cost and People (SQDCP) metrics. For each metric, record the target, actual performance and RAG status. Document issues raised and actions assigned. Set priorities for the day. Review open actions and update status.
MEETING DETAILS
Meeting Date
Facilitator
Attendees
Today's Priorities:
SQDCP — SAFETY, QUALITY, DELIVERY, COST, PEOPLE
Category | Metric | Target | Actual | RAG | Issue / Comment | Action | Owner
OPEN ACTIONS
Action | Owner | Due Date | Status
simplicityhub.co.uk |  |  | Daily Management Board ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB™ DAILY MANAGEMENT BOARD |  |  |  | PRACTICAL TEMPLATE
Structure your daily team standup — review SQDCP performance, surface issues, assign actions and set today's priorities. |  |  |  |  | DAILY MANAGEMENT BOARD
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS DAILY MANAGEMENT BOARD? | A Daily Management Board structures the daily team standup meeting, ensuring consistent review of Safety, Quality, Delivery, Cost and People (SQDCP) metrics. For each metric, record the target, actual performance and RAG status. Document issues raised and actions assigned. Set priorities for the day. Review open actions and update status.
MEETING DETAILS
Meeting Date | 07 Apr 2026
Facilitator | CS Team Lead
Attendees | All CS agents, James Carter (Project Owner), IT Lead (dial-in)
Today's Priorities: 1. Review CSAT acknowledgement SLA breaches from last week (6 cases) — identify common factor. 2. Confirm agent coaching session for checklist compliance — close this action. 3. IT update on CSAT trigger fix timeline.
SQDCP — SAFETY, QUALITY, DELIVERY, COST, PEOPLE
Category | Metric | Target | Actual | RAG | Issue / Comment | Action | Owner
Safety | Incidents or near misses today | 0 | 0 | Green | — | — | —
Quality | Investigation checklist compliance (yesterday) | 100% | 97% (11/12) | Amber | 1 agent not completing checklist — same agent as last week | Coaching session today at 14:00 — TL to confirm | CS Team Lead
Quality | CSAT score (last available — monthly) | ≥ 72% | 69% | Amber | Improving trend. Trigger fix still pending. | Chase IT for CSAT trigger update — today | CS Team Lead
Delivery | Acknowledgement within 4h — yesterday | 100% | 88% (7/8 cases) | Red | 6 cases breached 4h SLA last week — investigating common factor today | Review 6 breach cases — identify cause by 12:00 | James Carter
Delivery | Average TTR — last 7 days | ≤ 3.5 days | 3.8 days | Amber | Approaching target — positive direction | Monitor — no action required today | CS Team Lead
Delivery | Cases open >48 hours in queue | 0 | 3 | Amber | 3 cases approaching 48h — agents to pick up this morning | Agents to review and action queue now | CS Agent
Cost | Average handling time (AHT) — last 7 days | ≤ 12 min | 10.5 min | Green | Ahead of target | — | —
People | Attendance today | 100% (12) | 11/12 | Amber | 1 agent on planned leave today — TL to monitor queue capacity | TL to review daily capacity — consider reallocation | CS Team Lead
OPEN ACTIONS
Action | Owner | Due Date | Status
Review 6 SLA acknowledgement breach cases — identify common factor | James Carter | Today 12:00 | Open
Coaching session — investigation checklist compliance (1 agent) | CS Team Lead | Today 14:00 | Open
Chase IT for CSAT survey trigger update and confirm delivery date | CS Team Lead | Today | Open
All agents: clear queue of cases approaching 48-hour threshold | CS Agent | This morning | Open
IT: CSAT survey trigger deployment | IT Lead | 28 Apr 2026 | In Progress
simplicityhub.co.uk |  |  | Daily Management Board ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html