## Blank Template
SH | SIMPLICITYHUB™ KAIZEN EVENT PLANNER |  |  |  | PRACTICAL TEMPLATE
Plan a structured rapid improvement event — define the problem, target state, day-by-day agenda, team roles and outputs. |  |  |  |  | KAIZEN EVENT PLANNER
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
1.0
BUSINESS AREA
WHAT IS KAIZEN EVENT PLANNER? | A Kaizen Event Planner helps teams prepare for a focused rapid improvement event (Kaizen). It defines the event name, dates, area, problem statement, current state, target state, day-by-day agenda, team members and expected outputs. A well-planned Kaizen event produces tangible improvements in 1–5 days that would take months through conventional change approaches.
EVENT DETAILS
Event Name
Start Date
End Date
Area / Process
Facilitator
Sponsor
PROBLEM STATEMENT
CURRENT STATE
TARGET STATE
EVENT AGENDA |  |  | Day-by-day session plan
Day | Session | Activity / Focus | Facilitator | Expected Output
KAIZEN TEAM
Name | Role in Kaizen | Department
EXPECTED OUTPUTS FROM THE EVENT
FOLLOW-UP ACTIONS AND DATES
simplicityhub.co.uk |  |  | Kaizen Event Planner ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html

## Completed Example
SH | SIMPLICITYHUB™ KAIZEN EVENT PLANNER |  |  |  | PRACTICAL TEMPLATE
Plan a structured rapid improvement event — define the problem, target state, day-by-day agenda, team roles and outputs. |  |  |  |  | KAIZEN EVENT PLANNER
PROJECT TITLE | PROJECT OWNER | SPONSOR | VERSION | DATE | UPDATED BY
Customer Complaint Response Time Reduction | James Carter | Sarah Mitchell | 1.0 | 01 Apr 2026 | James Carter
BUSINESS AREA | Customer Service
WHAT IS KAIZEN EVENT PLANNER? | A Kaizen Event Planner helps teams prepare for a focused rapid improvement event (Kaizen). It defines the event name, dates, area, problem statement, current state, target state, day-by-day agenda, team members and expected outputs. A well-planned Kaizen event produces tangible improvements in 1–5 days that would take months through conventional change approaches.
EVENT DETAILS
Event Name | Complaint Investigation Deep Dive Kaizen
Start Date | 14 Jan 2026
End Date | 15 Jan 2026
Area / Process | Customer Service — Complaint Handling
Facilitator | James Carter
Sponsor | Sarah Mitchell
PROBLEM STATEMENT
Average complaint investigation time is 8.5 minutes per case with high variability across agents. There is no standard investigation approach — agents use personal methods, search multiple systems and frequently spend time looking for resolution authority. This drives long response times, high repeat contact rates and inconsistent customer outcomes.
CURRENT STATE
Average TTR: 5.2 days. Investigation time: avg 8.5 min, range 4–18 min. Agents switch between 3 systems. No standard process. No investigation checklist. Authority levels unclear — agents frequently escalating unnecessarily. Repeat contact rate 38%.
TARGET STATE
Standard investigation checklist designed and tested. Average investigation time ≤6 min. Authority levels defined and agreed. All agents able to resolve tier-1 complaints without escalation. Repeat contact rate target: ≤30% within 90 days of implementation.
EVENT AGENDA |  |  | Day-by-day session plan
Day | Session | Activity / Focus | Facilitator | Expected Output
Day 1 | Morning | Gemba observation — observe 5 live complaint investigations. Time each step. Map waste. | James Carter | Current state observation data and waste identification
Day 1 | Morning | Current state process map — build a visual map of all steps from complaint receipt to closure | James Carter | Current state process map with time data and waste points marked
Day 1 | Afternoon | Root cause analysis — why is investigation time so variable? 5 Whys and fishbone for top 3 drivers | James Carter | Agreed root causes — visual fishbone diagram
Day 1 | Afternoon | Future state design — agree what the ideal investigation process looks like. Define checklist structure | James Carter | Future state process map, checklist outline agreed by team
Day 2 | Morning | Co-design investigation checklist with CS agents — use real cases to test and iterate | James Carter | Draft investigation checklist — v1
Day 2 | Morning | Draft authority levels and escalation criteria guide — agree tier-based resolution with CS manager | James Carter | Authority levels guide — first draft reviewed by CS manager
Day 2 | Afternoon | Test investigation checklist on 10 live cases. Refine wording. Time the process. | James Carter | Refined investigation checklist — v2. Time confirmation: ≤6 min
Day 2 | Afternoon | Build implementation plan — owners, dates, training plan, control measures and go-live date | James Carter | Kaizen implementation plan — signed off by sponsor
KAIZEN TEAM
Name | Role in Kaizen | Department
James Carter | Kaizen Facilitator / Project Lead | Process Improvement
Sarah Mitchell | Sponsor — sign-off authority | Customer Service Director
CS Team Lead | Team Leader — process knowledge | Customer Service
CS Agent (x2) | Front-line — co-design checklist | Customer Service
IT Lead | Systems — CRM changes scoped | IT
L&D Lead | Training design and delivery | Learning & Development
EXPECTED OUTPUTS FROM THE EVENT
1. Investigation checklist (CRM-embedded, mandatory field) 2. Authority levels and escalation criteria guide 3. Standard closure communication script 4. Kaizen implementation plan with named owners and dates 5. Training plan for all 12 CS agents
FOLLOW-UP ACTIONS AND DATES
Go-live: 01 Apr 2026. Training week: 21 Apr 2026. First audit: 01 May 2026. TTR review at 30 days: 01 May 2026. Benefits review: 01 Jul 2026.
simplicityhub.co.uk |  |  | Kaizen Event Planner ¦ PRACTICAL TEMPLATE
© 2026 SimplicityHub. All rights reserved. Unauthorised reproduction or distribution is prohibited. |  |  |  | simplicityhub.co.uk/pages/terms.html